## Project Settings
/Non Project/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Project Settings
Project Owner | Javier Mesa
Start Date | mar 05, 2017 09:48:56 AM
Completion Date | mar 06, 2017 10:53:21 PM | Completed: *
Keywords
Language | Java
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:58 PM el 6/03/2017

## Overall Metrics
/Non Project/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 31 | 26.3 | 29.3
Planned Time | 0.15972 |  | 0.45139
Actual Tiempo |  | 0.14583 | 0.50069
CPI (Cost-Performance Index) |  |  | 0.9
% Reuse | 17.1% | 22.5% | 8.27%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 0 | 0 | 0
Total Defects/KLOC or equivalent | 38.8 | 21.7 | 34.1
Yield % | 81.9% | 100% | 66.7%
Code Review Rate | 238 | 240 | 918
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:57 PM el 6/03/2017

## Program Size
/Non Project/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 109 | 109 | 218
Deleted (D) | 68 | 84 | 174
Modified (M) | 10 | 0 | 19
Added (A) | 109 | 92 | 333
Reused (R) | 31 | 34 | 34
Added and Modified (A+M) | 119 | 92 | 352
Total Size (T) | 181 | 151 | 411
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 125 | 175 | 434
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:59 PM el 6/03/2017

## Time In Phase
/Non Project/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.055556 | 0.029861 | 0.11458 | 22.9%
DiseÃ±o | 0.018056 | 0.015278 | 0.080556 | 16.1%
RevisiÃ³n de DiseÃ±o | 0.0083333 | 0.0090278 | 0.0090278 | 1.8%
CodificaciÃ³n | 0.034722 | 0.042361 | 0.18611 | 37.2%
RevisiÃ³n de CodificaciÃ³n | 0.020833 | 0.015972 | 0.015972 | 3.19%
CompilaciÃ³n | 0.0069444 | 0.0090278 | 0.047222 | 9.43%
Pruebas | 0.011111 | 0.018056 | 0.031944 | 6.38%
Postmortem | 0.0041667 | 0.00625 | 0.015278 | 3.05%
Total | 0.15972 | 0.14583 | 0.50069
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:59 PM el 6/03/2017

## Defects Injected
/Non Project/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0 | 1 | 1 | 8.33%
DiseÃ±o | 2.28 | 1 | 6 | 50%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 2.28 | 0 | 5 | 41.7%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 4.57 | 2 | 12
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:00 PM el 6/03/2017

## Defects Removed
/Non Project/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 0 | 1 | 1 | 8.33%
CodificaciÃ³n | 2.74 | 1 | 7 | 58.3%
RevisiÃ³n de CodificaciÃ³n | 1 | 0 | 0 | 0%
CompilaciÃ³n | 0.87 | 0 | 4 | 33.3%
Pruebas | 0 | 0 | 0 | 0%
Total | 4.61 | 2 | 12
After Development | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:00 PM el 6/03/2017

## Defect Removal Efficiency
/Non Project/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 0 | 4.62 | 4.62
Defects/Hour - Code Review | 2 | 0 | 0
Defects/Hour - Compile | 5.22 | 0 | 3.53
Defects/Hour - Test | 0 | 0 | 0
DRL (DLDR/UT) | #VALUE! | #DIV/0! | #DIV/0!
DRL (Code Review/UT) | #VALUE! | #DIV/0! | #DIV/0!
DRL (Compile/UT) | #VALUE! | #DIV/0! | #DIV/0!
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:00 PM el 6/03/2017